## Skyline
Activity ID | Subsystem ID | Subsystem Description | Station | RFC Date | RFC Progress % | ITRs Closed | Total ITRs
BMT-RFC-0010 | BMT-61-01 | Instrument & Utility Air - Subsystem 61-01 | Bahari Marine Terminal | 2026-05-30 | 100% | 22 | 22
BMT-RFC-0020 | BMT-06-01 | Lighting & Small Power - Subsystem 06-01 | Bahari Marine Terminal | 2026-06-09 | 100% | 29 | 29
BMT-RFC-0030 | BMT-62-01 | Diesel Fuel - Subsystem 62-01 | Bahari Marine Terminal | 2026-06-09 | 100% | 45 | 45
BMT-RFC-0050 | BMT-03-01 | HV Power Distribution - Subsystem 03-01 | Bahari Marine Terminal | 2026-06-14 | 100% | 50 | 50
BMT-RFC-0040 | BMT-04-01 | LV Power Distribution - Subsystem 04-01 | Bahari Marine Terminal | 2026-06-22 | 100% | 35 | 35
BMT-RFC-0060 | BMT-61-02 | Instrument & Utility Air - Subsystem 61-02 | Bahari Marine Terminal | 2026-06-22 | 100% | 25 | 25
BMT-RFC-0070 | BMT-63-01 | Potable & Utility Water - Subsystem 63-01 | Bahari Marine Terminal | 2026-06-25 | 100% | 69 | 69
BMT-RFC-0100 | BMT-83-01 | Control Buildings - Subsystem 83-01 | Bahari Marine Terminal | 2026-06-28 | 62.5% | 15 | 24
BMT-RFC-0090 | BMT-60-02 | Heat Tracing - Subsystem 60-02 | Bahari Marine Terminal | 2026-07-02 | 100% | 47 | 47
BMT-RFC-0080 | BMT-60-01 | Heat Tracing - Subsystem 60-01 | Bahari Marine Terminal | 2026-07-08 | 100% | 14 | 14
BMT-RFC-0110 | BMT-60-03 | Heat Tracing - Subsystem 60-03 | Bahari Marine Terminal | 2026-07-09 | 78.95% | 15 | 19
BMT-RFC-0120 | BMT-60-04 | Heat Tracing - Subsystem 60-04 | Bahari Marine Terminal | 2026-07-17 | 100% | 49 | 49
BMT-RFC-0130 | BMT-60-05 | Heat Tracing - Subsystem 60-05 | Bahari Marine Terminal | 2026-07-19 | 100% | 51 | 51
BMT-RFC-0150 | BMT-71-01 | Firewater Pumps & Ring Main - Subsystem 71-01 | Bahari Marine Terminal | 2026-07-22 | 78.57% | 22 | 28
BMT-RFC-0200 | BMT-61-03 | Instrument & Utility Air - Subsystem 61-03 | Bahari Marine Terminal | 2026-07-31 | 100% | 66 | 66
BMT-RFC-0170 | BMT-60-08 | Heat Tracing - Subsystem 60-08 | Bahari Marine Terminal | 2026-08-02 | 100% | 18 | 18
BMT-RFC-0190 | BMT-60-10 | Heat Tracing - Subsystem 60-10 | Bahari Marine Terminal | 2026-08-02 | 61.29% | 19 | 31
BMT-RFC-0220 | BMT-60-12 | Heat Tracing - Subsystem 60-12 | Bahari Marine Terminal | 2026-08-02 | 86.05% | 37 | 43
BMT-RFC-0140 | BMT-60-06 | Heat Tracing - Subsystem 60-06 | Bahari Marine Terminal | 2026-08-05 | 100% | 54 | 54
BMT-RFC-0270 | BMT-74-01 | Gaseous Fire Suppression - Subsystem 74-01 | Bahari Marine Terminal | 2026-08-09 | 53.49% | 23 | 43
BMT-RFC-0160 | BMT-60-07 | Heat Tracing - Subsystem 60-07 | Bahari Marine Terminal | 2026-08-10 | 86.67% | 13 | 15
BMT-RFC-0180 | BMT-60-09 | Heat Tracing - Subsystem 60-09 | Bahari Marine Terminal | 2026-08-12 | 53.33% | 8 | 15
BMT-RFC-0250 | BMT-60-14 | Heat Tracing - Subsystem 60-14 | Bahari Marine Terminal | 2026-08-12 | 67.65% | 46 | 68
BMT-RFC-0260 | BMT-62-02 | Diesel Fuel - Subsystem 62-02 | Bahari Marine Terminal | 2026-08-13 | 88.46% | 23 | 26
BMT-RFC-0210 | BMT-60-11 | Heat Tracing - Subsystem 60-11 | Bahari Marine Terminal | 2026-08-14 | 64.29% | 27 | 42
BMT-RFC-0340 | BMT-60-17 | Heat Tracing - Subsystem 60-17 | Bahari Marine Terminal | 2026-08-23 | 34.21% | 13 | 38
BMT-RFC-0280 | BMT-04-02 | LV Power Distribution - Subsystem 04-02 | Bahari Marine Terminal | 2026-08-25 | 35% | 7 | 20
BMT-RFC-0230 | BMT-61-04 | Instrument & Utility Air - Subsystem 61-04 | Bahari Marine Terminal | 2026-08-26 | 58.54% | 24 | 41
BMT-RFC-0310 | BMT-03-02 | HV Power Distribution - Subsystem 03-02 | Bahari Marine Terminal | 2026-08-28 | 75% | 21 | 28
BMT-RFC-0320 | BMT-09-01 | Fire & Gas Detection - Subsystem 09-01 | Bahari Marine Terminal | 2026-08-29 | 52.83% | 28 | 53
BMT-RFC-0440 | BMT-71-03 | Firewater Pumps & Ring Main - Subsystem 71-03 | Bahari Marine Terminal | 2026-08-30 | 43.1% | 25 | 58
BMT-RFC-0360 | BMT-61-06 | Instrument & Utility Air - Subsystem 61-06 | Bahari Marine Terminal | 2026-08-31 | 88.64% | 39 | 44
BMT-RFC-0240 | BMT-60-13 | Heat Tracing - Subsystem 60-13 | Bahari Marine Terminal | 2026-09-01 | 40.91% | 27 | 66
BMT-RFC-0420 | BMT-60-18 | Heat Tracing - Subsystem 60-18 | Bahari Marine Terminal | 2026-09-04 | 77.27% | 17 | 22
BMT-RFC-0380 | BMT-73-02 | Foam & Deluge - Subsystem 73-02 | Bahari Marine Terminal | 2026-09-05 | 50% | 10 | 20
BMT-RFC-0410 | BMT-53-01 | Fired Heaters - Subsystem 53-01 | Bahari Marine Terminal | 2026-09-06 | 30.77% | 4 | 13
BMT-RFC-0490 | BMT-20-02 | Crude Transfer - Subsystem 20-02 | Bahari Marine Terminal | 2026-09-07 | 65.85% | 27 | 41
BMT-RFC-0500 | BMT-20-03 | Crude Transfer - Subsystem 20-03 | Bahari Marine Terminal | 2026-09-07 | 80% | 8 | 10
BMT-RFC-0290 | BMT-60-15 | Heat Tracing - Subsystem 60-15 | Bahari Marine Terminal | 2026-09-08 | 65.62% | 21 | 32
BMT-RFC-0330 | BMT-60-16 | Heat Tracing - Subsystem 60-16 | Bahari Marine Terminal | 2026-09-08 | 30% | 9 | 30
BMT-RFC-0300 | BMT-63-02 | Potable & Utility Water - Subsystem 63-02 | Bahari Marine Terminal | 2026-09-09 | 71.43% | 5 | 7
BMT-RFC-0370 | BMT-73-01 | Foam & Deluge - Subsystem 73-01 | Bahari Marine Terminal | 2026-09-10 | 50% | 19 | 38
BMT-RFC-0450 | BMT-71-04 | Firewater Pumps & Ring Main - Subsystem 71-04 | Bahari Marine Terminal | 2026-09-11 | 25% | 16 | 64
BMT-RFC-0390 | BMT-01-01 | Main Power Generation - Subsystem 01-01 | Bahari Marine Terminal | 2026-09-12 | 30.77% | 4 | 13
BMT-RFC-0350 | BMT-61-05 | Instrument & Utility Air - Subsystem 61-05 | Bahari Marine Terminal | 2026-09-12 | 50% | 6 | 12
BMT-RFC-0430 | BMT-71-02 | Firewater Pumps & Ring Main - Subsystem 71-02 | Bahari Marine Terminal | 2026-09-13 | 50% | 3 | 6
BMT-RFC-0590 | BMT-60-21 | Heat Tracing - Subsystem 60-21 | Bahari Marine Terminal | 2026-09-15 | 33.33% | 25 | 75
BMT-RFC-0460 | BMT-01-02 | Main Power Generation - Subsystem 01-02 | Bahari Marine Terminal | 2026-09-18 | 57.14% | 4 | 7
BMT-RFC-0470 | BMT-01-03 | Main Power Generation - Subsystem 01-03 | Bahari Marine Terminal | 2026-09-19 | 67.78% | 61 | 90
BMT-RFC-0400 | BMT-04-03 | LV Power Distribution - Subsystem 04-03 | Bahari Marine Terminal | 2026-09-19 | 74.07% | 20 | 27
BMT-RFC-0660 | BMT-61-07 | Instrument & Utility Air - Subsystem 61-07 | Bahari Marine Terminal | 2026-09-20 | 80% | 20 | 25
BMT-RFC-0680 | BMT-73-04 | Foam & Deluge - Subsystem 73-04 | Bahari Marine Terminal | 2026-09-20 | 26.67% | 12 | 45
BMT-RFC-0550 | BMT-04-04 | LV Power Distribution - Subsystem 04-04 | Bahari Marine Terminal | 2026-09-21 | 42.86% | 3 | 7
BMT-RFC-0650 | BMT-08-02 | ICSS & Control Systems - Subsystem 08-02 | Bahari Marine Terminal | 2026-09-21 | 41.67% | 5 | 12
BMT-RFC-0510 | BMT-28-01 | Mainline Pumps - Subsystem 28-01 | Bahari Marine Terminal | 2026-09-22 | 56.25% | 9 | 16
BMT-RFC-0530 | BMT-60-19 | Heat Tracing - Subsystem 60-19 | Bahari Marine Terminal | 2026-09-24 | 57.14% | 8 | 14
BMT-RFC-0560 | BMT-04-05 | LV Power Distribution - Subsystem 04-05 | Bahari Marine Terminal | 2026-09-25 | 57.14% | 4 | 7
BMT-RFC-0670 | BMT-73-03 | Foam & Deluge - Subsystem 73-03 | Bahari Marine Terminal | 2026-09-25 | 47.83% | 33 | 69
BMT-RFC-0540 | BMT-01-04 | Main Power Generation - Subsystem 01-04 | Bahari Marine Terminal | 2026-09-26 | 42.59% | 23 | 54
BMT-RFC-0630 | BMT-03-05 | HV Power Distribution - Subsystem 03-05 | Bahari Marine Terminal | 2026-09-26 | 60.42% | 29 | 48
BMT-RFC-0480 | BMT-20-01 | Crude Transfer - Subsystem 20-01 | Bahari Marine Terminal | 2026-09-27 | 40.43% | 19 | 47
BMT-RFC-0520 | BMT-28-02 | Mainline Pumps - Subsystem 28-02 | Bahari Marine Terminal | 2026-09-27 | 76.32% | 58 | 76
BMT-RFC-0640 | BMT-08-01 | ICSS & Control Systems - Subsystem 08-01 | Bahari Marine Terminal | 2026-09-28 | 75.76% | 25 | 33
BMT-RFC-0580 | BMT-60-20 | Heat Tracing - Subsystem 60-20 | Bahari Marine Terminal | 2026-09-30 | 78.95% | 15 | 19
BMT-RFC-0600 | BMT-62-03 | Diesel Fuel - Subsystem 62-03 | Bahari Marine Terminal | 2026-09-30 | 79.1% | 53 | 67
BMT-RFC-0730 | BMT-73-05 | Foam & Deluge - Subsystem 73-05 | Bahari Marine Terminal | 2026-09-30 | 50% | 14 | 28
BMT-RFC-0740 | BMT-73-06 | Foam & Deluge - Subsystem 73-06 | Bahari Marine Terminal | 2026-10-03 | 41.89% | 31 | 74
BMT-RFC-0720 | BMT-61-09 | Instrument & Utility Air - Subsystem 61-09 | Bahari Marine Terminal | 2026-10-04 | 67.8% | 40 | 59
BMT-RFC-0750 | BMT-73-07 | Foam & Deluge - Subsystem 73-07 | Bahari Marine Terminal | 2026-10-04 | 50% | 5 | 10
BMT-RFC-0700 | BMT-08-04 | ICSS & Control Systems - Subsystem 08-04 | Bahari Marine Terminal | 2026-10-06 | 58.82% | 10 | 17
BMT-RFC-0570 | BMT-28-03 | Mainline Pumps - Subsystem 28-03 | Bahari Marine Terminal | 2026-10-07 | 31.25% | 15 | 48
BMT-RFC-0800 | BMT-61-10 | Instrument & Utility Air - Subsystem 61-10 | Bahari Marine Terminal | 2026-10-07 | 40.91% | 9 | 22
BMT-RFC-0690 | BMT-08-03 | ICSS & Control Systems - Subsystem 08-03 | Bahari Marine Terminal | 2026-10-08 | 32.43% | 12 | 37
BMT-RFC-0710 | BMT-61-08 | Instrument & Utility Air - Subsystem 61-08 | Bahari Marine Terminal | 2026-10-08 | 34.78% | 8 | 23
BMT-RFC-0610 | BMT-03-03 | HV Power Distribution - Subsystem 03-03 | Bahari Marine Terminal | 2026-10-10 | 56.76% | 21 | 37
BMT-RFC-0620 | BMT-03-04 | HV Power Distribution - Subsystem 03-04 | Bahari Marine Terminal | 2026-10-11 | 40.82% | 20 | 49
BMT-RFC-0880 | BMT-24-03 | Pig Launching & Receiving - Subsystem 24-03 | Bahari Marine Terminal | 2026-10-11 | 69.57% | 16 | 23
BMT-RFC-0760 | BMT-08-05 | ICSS & Control Systems - Subsystem 08-05 | Bahari Marine Terminal | 2026-10-12 | 50% | 7 | 14
BMT-RFC-0780 | BMT-24-01 | Pig Launching & Receiving - Subsystem 24-01 | Bahari Marine Terminal | 2026-10-12 | 47.83% | 11 | 23
BMT-RFC-0830 | BMT-62-04 | Diesel Fuel - Subsystem 62-04 | Bahari Marine Terminal | 2026-10-15 | 80% | 4 | 5
BMT-RFC-0900 | BMT-73-08 | Foam & Deluge - Subsystem 73-08 | Bahari Marine Terminal | 2026-10-17 | 77.14% | 27 | 35
BMT-RFC-0960 | BMT-28-04 | Mainline Pumps - Subsystem 28-04 | Bahari Marine Terminal | 2026-10-18 | 75% | 3 | 4
BMT-RFC-0850 | BMT-03-06 | HV Power Distribution - Subsystem 03-06 | Bahari Marine Terminal | 2026-10-20 | 44.12% | 15 | 34
BMT-RFC-0770 | BMT-08-06 | ICSS & Control Systems - Subsystem 08-06 | Bahari Marine Terminal | 2026-10-21 | 73.08% | 19 | 26
BMT-RFC-0930 | BMT-04-06 | LV Power Distribution - Subsystem 04-06 | Bahari Marine Terminal | 2026-10-22 | 30.77% | 8 | 26
BMT-RFC-0870 | BMT-08-08 | ICSS & Control Systems - Subsystem 08-08 | Bahari Marine Terminal | 2026-10-23 | 56.1% | 23 | 41
BMT-RFC-0820 | BMT-61-12 | Instrument & Utility Air - Subsystem 61-12 | Bahari Marine Terminal | 2026-10-25 | 62.26% | 66 | 106
BMT-RFC-0810 | BMT-61-11 | Instrument & Utility Air - Subsystem 61-11 | Bahari Marine Terminal | 2026-10-26 | 70.37% | 19 | 27
BMT-RFC-0790 | BMT-24-02 | Pig Launching & Receiving - Subsystem 24-02 | Bahari Marine Terminal | 2026-10-27 | 78.79% | 52 | 66
BMT-RFC-0840 | BMT-02-01 | Emergency Diesel Generation - Subsystem 02-01 | Bahari Marine Terminal | 2026-10-30 | 33.33% | 2 | 6
BMT-RFC-0950 | BMT-24-04 | Pig Launching & Receiving - Subsystem 24-04 | Bahari Marine Terminal | 2026-10-30 | 37.5% | 12 | 32
BMT-RFC-0890 | BMT-53-02 | Fired Heaters - Subsystem 53-02 | Bahari Marine Terminal | 2026-10-30 | 26.53% | 13 | 49
BMT-RFC-1010 | BMT-73-09 | Foam & Deluge - Subsystem 73-09 | Bahari Marine Terminal | 2026-10-30 | 17.74% | 11 | 62
BMT-RFC-0940 | BMT-05-01 | UPS & DC Systems - Subsystem 05-01 | Bahari Marine Terminal | 2026-10-31 | 40.87% | 47 | 115
BMT-RFC-1020 | BMT-99-01 | Commissioning Support - Subsystem 99-01 | Bahari Marine Terminal | 2026-11-01 | 44.44% | 28 | 63
BMT-RFC-0860 | BMT-08-07 | ICSS & Control Systems - Subsystem 08-07 | Bahari Marine Terminal | 2026-11-02 | 25% | 6 | 24
BMT-RFC-1050 | BMT-01-07 | Main Power Generation - Subsystem 01-07 | Bahari Marine Terminal | 2026-11-03 | 41.18% | 7 | 17
BMT-RFC-0970 | BMT-01-05 | Main Power Generation - Subsystem 01-05 | Bahari Marine Terminal | 2026-11-08 | 50% | 7 | 14
BMT-RFC-0980 | BMT-02-02 | Emergency Diesel Generation - Subsystem 02-02 | Bahari Marine Terminal | 2026-11-08 | 33.33% | 4 | 12
BMT-RFC-1150 | BMT-62-09 | Diesel Fuel - Subsystem 62-09 | Bahari Marine Terminal | 2026-11-09 | 30% | 6 | 20
BMT-RFC-1030 | BMT-99-02 | Commissioning Support - Subsystem 99-02 | Bahari Marine Terminal | 2026-11-09 | 9.524% | 4 | 42
BMT-RFC-1040 | BMT-01-06 | Main Power Generation - Subsystem 01-06 | Bahari Marine Terminal | 2026-11-10 | 47.37% | 9 | 19
BMT-RFC-0910 | BMT-03-07 | HV Power Distribution - Subsystem 03-07 | Bahari Marine Terminal | 2026-11-10 | 22.86% | 8 | 35
BMT-RFC-1140 | BMT-62-08 | Diesel Fuel - Subsystem 62-08 | Bahari Marine Terminal | 2026-11-10 | 29.27% | 12 | 41
BMT-RFC-0920 | BMT-03-08 | HV Power Distribution - Subsystem 03-08 | Bahari Marine Terminal | 2026-11-11 | 47.37% | 9 | 19
BMT-RFC-0990 | BMT-09-02 | Fire & Gas Detection - Subsystem 09-02 | Bahari Marine Terminal | 2026-11-11 | 49.62% | 129 | 260
BMT-RFC-1000 | BMT-24-05 | Pig Launching & Receiving - Subsystem 24-05 | Bahari Marine Terminal | 2026-11-13 | 27.27% | 3 | 11
BMT-RFC-1130 | BMT-62-07 | Diesel Fuel - Subsystem 62-07 | Bahari Marine Terminal | 2026-11-13 | 38.46% | 50 | 130
BMT-RFC-1070 | BMT-03-10 | HV Power Distribution - Subsystem 03-10 | Bahari Marine Terminal | 2026-11-15 | 25% | 7 | 28
BMT-RFC-1190 | BMT-28-05 | Mainline Pumps - Subsystem 28-05 | Bahari Marine Terminal | 2026-11-16 | 36.84% | 7 | 19
BMT-RFC-1100 | BMT-08-09 | ICSS & Control Systems - Subsystem 08-09 | Bahari Marine Terminal | 2026-11-17 | 42.71% | 41 | 96
BMT-RFC-1220 | BMT-61-13 | Instrument & Utility Air - Subsystem 61-13 | Bahari Marine Terminal | 2026-11-18 | 21.15% | 11 | 52
BMT-RFC-1160 | BMT-62-10 | Diesel Fuel - Subsystem 62-10 | Bahari Marine Terminal | 2026-11-18 | 43.1% | 25 | 58
BMT-RFC-1120 | BMT-62-06 | Diesel Fuel - Subsystem 62-06 | Bahari Marine Terminal | 2026-11-20 | 25% | 4 | 16
BMT-RFC-1060 | BMT-03-09 | HV Power Distribution - Subsystem 03-09 | Bahari Marine Terminal | 2026-11-23 | 18.75% | 3 | 16
BMT-RFC-1080 | BMT-25-01 | Metering - Subsystem 25-01 | Bahari Marine Terminal | 2026-11-25 | 47.92% | 23 | 48
BMT-RFC-1090 | BMT-25-02 | Metering - Subsystem 25-02 | Bahari Marine Terminal | 2026-11-25 | 52.5% | 21 | 40
BMT-RFC-1110 | BMT-62-05 | Diesel Fuel - Subsystem 62-05 | Bahari Marine Terminal | 2026-11-25 | 28.12% | 9 | 32
BMT-RFC-1210 | BMT-53-04 | Fired Heaters - Subsystem 53-04 | Bahari Marine Terminal | 2026-11-26 | 40% | 4 | 10
BMT-RFC-1170 | BMT-01-08 | Main Power Generation - Subsystem 01-08 | Bahari Marine Terminal | 2026-11-28 | 4.545% | 1 | 22
BMT-RFC-1260 | BMT-79-02 | Telecom - Subsystem 79-02 | Bahari Marine Terminal | 2026-12-01 | 10.91% | 12 | 110
BMT-RFC-1330 | BMT-79-09 | Telecom - Subsystem 79-09 | Bahari Marine Terminal | 2026-12-01 | 42.11% | 8 | 19
BMT-RFC-1180 | BMT-01-09 | Main Power Generation - Subsystem 01-09 | Bahari Marine Terminal | 2026-12-02 | 54.55% | 12 | 22
BMT-RFC-1200 | BMT-53-03 | Fired Heaters - Subsystem 53-03 | Bahari Marine Terminal | 2026-12-03 | 18.27% | 19 | 104
BMT-RFC-1280 | BMT-79-04 | Telecom - Subsystem 79-04 | Bahari Marine Terminal | 2026-12-03 | 30% | 3 | 10
BMT-RFC-1240 | BMT-25-04 | Metering - Subsystem 25-04 | Bahari Marine Terminal | 2026-12-04 | 10% | 2 | 20
BMT-RFC-1230 | BMT-25-03 | Metering - Subsystem 25-03 | Bahari Marine Terminal | 2026-12-10 | 41.67% | 5 | 12
BMT-RFC-1270 | BMT-79-03 | Telecom - Subsystem 79-03 | Bahari Marine Terminal | 2026-12-10 | 27.12% | 16 | 59
BMT-RFC-1290 | BMT-79-05 | Telecom - Subsystem 79-05 | Bahari Marine Terminal | 2026-12-12 | 26.62% | 41 | 154
BMT-RFC-1480 | BMT-71-06 | Firewater Pumps & Ring Main - Subsystem 71-06 | Bahari Marine Terminal | 2026-12-13 | 27.5% | 11 | 40
BMT-RFC-1250 | BMT-79-01 | Telecom - Subsystem 79-01 | Bahari Marine Terminal | 2026-12-14 | 40% | 24 | 60
BMT-RFC-1390 | BMT-79-11 | Telecom - Subsystem 79-11 | Bahari Marine Terminal | 2026-12-15 | 22.22% | 2 | 9
BMT-RFC-1430 | BMT-08-11 | ICSS & Control Systems - Subsystem 08-11 | Bahari Marine Terminal | 2026-12-16 | 42.22% | 19 | 45
BMT-RFC-1350 | BMT-27-01 | Export Pumps - Subsystem 27-01 | Bahari Marine Terminal | 2026-12-16 | 47.37% | 9 | 19
BMT-RFC-1360 | BMT-53-05 | Fired Heaters - Subsystem 53-05 | Bahari Marine Terminal | 2026-12-16 | 46.67% | 7 | 15
BMT-RFC-1310 | BMT-79-07 | Telecom - Subsystem 79-07 | Bahari Marine Terminal | 2026-12-16 | 46.97% | 31 | 66
BMT-RFC-1320 | BMT-79-08 | Telecom - Subsystem 79-08 | Bahari Marine Terminal | 2026-12-17 | 50% | 2 | 4
BMT-RFC-1340 | BMT-79-10 | Telecom - Subsystem 79-10 | Bahari Marine Terminal | 2026-12-17 | 7.143% | 3 | 42
BMT-RFC-1450 | BMT-61-14 | Instrument & Utility Air - Subsystem 61-14 | Bahari Marine Terminal | 2026-12-19 | 19.05% | 4 | 21
BMT-RFC-1440 | BMT-08-12 | ICSS & Control Systems - Subsystem 08-12 | Bahari Marine Terminal | 2026-12-21 | 8.824% | 3 | 34
BMT-RFC-1420 | BMT-08-10 | ICSS & Control Systems - Subsystem 08-10 | Bahari Marine Terminal | 2026-12-22 | 13.64% | 3 | 22
BMT-RFC-1300 | BMT-79-06 | Telecom - Subsystem 79-06 | Bahari Marine Terminal | 2026-12-22 | 36.11% | 13 | 36
BMT-RFC-1500 | BMT-04-07 | LV Power Distribution - Subsystem 04-07 | Bahari Marine Terminal | 2026-12-23 | 8.696% | 6 | 69
BMT-RFC-1370 | BMT-63-03 | Potable & Utility Water - Subsystem 63-03 | Bahari Marine Terminal | 2026-12-23 | 38.71% | 12 | 31
BMT-RFC-1400 | BMT-99-03 | Commissioning Support - Subsystem 99-03 | Bahari Marine Terminal | 2026-12-24 | 22.73% | 5 | 22
BMT-RFC-1490 | BMT-03-11 | HV Power Distribution - Subsystem 03-11 | Bahari Marine Terminal | 2026-12-25 | 48.05% | 37 | 77
BMT-RFC-1380 | BMT-71-05 | Firewater Pumps & Ring Main - Subsystem 71-05 | Bahari Marine Terminal | 2026-12-26 | 5.357% | 3 | 56
BMT-RFC-1520 | BMT-26-01 | Crude Storage - Subsystem 26-01 | Bahari Marine Terminal | 2026-12-29 | 33.33% | 5 | 15
BMT-RFC-1600 | BMT-71-08 | Firewater Pumps & Ring Main - Subsystem 71-08 | Bahari Marine Terminal | 2026-12-29 | 38.3% | 36 | 94
BMT-RFC-1410 | BMT-99-04 | Commissioning Support - Subsystem 99-04 | Bahari Marine Terminal | 2026-12-29 | 27.78% | 10 | 36
BMT-RFC-1470 | BMT-64-01 | Sewage Treatment - Subsystem 64-01 | Bahari Marine Terminal | 2026-12-30 | 9.859% | 7 | 71
BMT-RFC-1570 | BMT-28-06 | Mainline Pumps - Subsystem 28-06 | Bahari Marine Terminal | 2027-01-01 | 14.29% | 2 | 14
BMT-RFC-1530 | BMT-61-15 | Instrument & Utility Air - Subsystem 61-15 | Bahari Marine Terminal | 2027-01-02 | 16.67% | 11 | 66
BMT-RFC-1610 | BMT-79-12 | Telecom - Subsystem 79-12 | Bahari Marine Terminal | 2027-01-02 | 38.46% | 10 | 26
BMT-RFC-1590 | BMT-28-08 | Mainline Pumps - Subsystem 28-08 | Bahari Marine Terminal | 2027-01-03 | 50% | 11 | 22
BMT-RFC-1650 | BMT-25-07 | Metering - Subsystem 25-07 | Bahari Marine Terminal | 2027-01-04 | 15.79% | 6 | 38
BMT-RFC-1460 | BMT-62-11 | Diesel Fuel - Subsystem 62-11 | Bahari Marine Terminal | 2027-01-04 | 54.29% | 19 | 35
BMT-RFC-1540 | BMT-62-12 | Diesel Fuel - Subsystem 62-12 | Bahari Marine Terminal | 2027-01-05 | 20% | 1 | 5
BMT-RFC-1550 | BMT-71-07 | Firewater Pumps & Ring Main - Subsystem 71-07 | Bahari Marine Terminal | 2027-01-07 | 42% | 21 | 50
BMT-RFC-1510 | BMT-09-03 | Fire & Gas Detection - Subsystem 09-03 | Bahari Marine Terminal | 2027-01-09 | 45.45% | 20 | 44
BMT-RFC-1580 | BMT-28-07 | Mainline Pumps - Subsystem 28-07 | Bahari Marine Terminal | 2027-01-09 | 17.86% | 5 | 28
BMT-RFC-1620 | BMT-05-02 | UPS & DC Systems - Subsystem 05-02 | Bahari Marine Terminal | 2027-01-11 | 41.18% | 7 | 17
BMT-RFC-1640 | BMT-25-06 | Metering - Subsystem 25-06 | Bahari Marine Terminal | 2027-01-12 | 9.091% | 3 | 33
BMT-RFC-1560 | BMT-73-10 | Foam & Deluge - Subsystem 73-10 | Bahari Marine Terminal | 2027-01-13 | 36.84% | 7 | 19
BMT-RFC-1690 | BMT-03-12 | HV Power Distribution - Subsystem 03-12 | Bahari Marine Terminal | 2027-01-18 | 36.36% | 4 | 11
BMT-RFC-1730 | BMT-63-04 | Potable & Utility Water - Subsystem 63-04 | Bahari Marine Terminal | 2027-01-18 | 20% | 6 | 30
BMT-RFC-1710 | BMT-99-05 | Commissioning Support - Subsystem 99-05 | Bahari Marine Terminal | 2027-01-20 | 21.76% | 37 | 170
BMT-RFC-1630 | BMT-25-05 | Metering - Subsystem 25-05 | Bahari Marine Terminal | 2027-01-21 | 28.26% | 26 | 92
BMT-RFC-1660 | BMT-86-01 | Site Security - Subsystem 86-01 | Bahari Marine Terminal | 2027-01-24 | 52.04% | 51 | 98
BMT-RFC-1700 | BMT-83-02 | Control Buildings - Subsystem 83-02 | Bahari Marine Terminal | 2027-01-25 | 25.23% | 28 | 111
BMT-RFC-1780 | BMT-09-05 | Fire & Gas Detection - Subsystem 09-05 | Bahari Marine Terminal | 2027-01-31 | 33.33% | 7 | 21
BMT-RFC-1670 | BMT-01-10 | Main Power Generation - Subsystem 01-10 | Bahari Marine Terminal | 2027-02-03 | 6.667% | 3 | 45
BMT-RFC-1680 | BMT-01-11 | Main Power Generation - Subsystem 01-11 | Bahari Marine Terminal | 2027-02-03 | 30.77% | 4 | 13
BMT-RFC-1800 | BMT-62-14 | Diesel Fuel - Subsystem 62-14 | Bahari Marine Terminal | 2027-02-03 | 52.38% | 22 | 42
BMT-RFC-1750 | BMT-80-01 | Buildings - Subsystem 80-01 | Bahari Marine Terminal | 2027-02-03 | 32.26% | 10 | 31
BMT-RFC-1720 | BMT-62-13 | Diesel Fuel - Subsystem 62-13 | Bahari Marine Terminal | 2027-02-08 | 21.88% | 7 | 32
BMT-RFC-1740 | BMT-63-05 | Potable & Utility Water - Subsystem 63-05 | Bahari Marine Terminal | 2027-02-10 | 20% | 5 | 25
BMT-RFC-1760 | BMT-61-16 | Instrument & Utility Air - Subsystem 61-16 | Bahari Marine Terminal | 2027-02-12 | 5.952% | 5 | 84
BMT-RFC-1820 | BMT-03-14 | HV Power Distribution - Subsystem 03-14 | Bahari Marine Terminal | 2027-02-14 | 0% | 0 | 30
BMT-RFC-1850 | BMT-08-13 | ICSS & Control Systems - Subsystem 08-13 | Bahari Marine Terminal | 2027-02-14 | 28.57% | 6 | 21
BMT-RFC-1810 | BMT-03-13 | HV Power Distribution - Subsystem 03-13 | Bahari Marine Terminal | 2027-02-16 | 30.3% | 10 | 33
BMT-RFC-1770 | BMT-09-04 | Fire & Gas Detection - Subsystem 09-04 | Bahari Marine Terminal | 2027-02-17 | 12.5% | 2 | 16
BMT-RFC-1790 | BMT-61-17 | Instrument & Utility Air - Subsystem 61-17 | Bahari Marine Terminal | 2027-02-17 | 3.571% | 1 | 28
BMT-RFC-1840 | BMT-82-02 | Substations - Subsystem 82-02 | Bahari Marine Terminal | 2027-02-20 | 0% | 0 | 11
BMT-RFC-1880 | BMT-84-01 | Warehouse & Workshops - Subsystem 84-01 | Bahari Marine Terminal | 2027-02-20 | 10% | 1 | 10
BMT-RFC-1830 | BMT-82-01 | Substations - Subsystem 82-01 | Bahari Marine Terminal | 2027-02-26 | 8.333% | 3 | 36
BMT-RFC-1860 | BMT-08-14 | ICSS & Control Systems - Subsystem 08-14 | Bahari Marine Terminal | 2027-03-01 | 9.877% | 8 | 81
BMT-RFC-1870 | BMT-82-03 | Substations - Subsystem 82-03 | Bahari Marine Terminal | 2027-03-10 | 0% | 0 | 36
KPS-RFC-0020 | KPS-04-01 | LV Power Distribution - Subsystem 04-01 | Kivuli Pump Station | 2026-06-16 | 100% | 75 | 75
KPS-RFC-0010 | KPS-06-01 | Lighting & Small Power - Subsystem 06-01 | Kivuli Pump Station | 2026-06-24 | 100% | 71 | 71
KPS-RFC-0040 | KPS-04-02 | LV Power Distribution - Subsystem 04-02 | Kivuli Pump Station | 2026-07-01 | 100% | 44 | 44
KPS-RFC-0030 | KPS-62-01 | Diesel Fuel - Subsystem 62-01 | Kivuli Pump Station | 2026-07-03 | 68.18% | 15 | 22
KPS-RFC-0070 | KPS-03-01 | HV Power Distribution - Subsystem 03-01 | Kivuli Pump Station | 2026-07-09 | 100% | 13 | 13
KPS-RFC-0050 | KPS-91-01 | Drainage - Subsystem 91-01 | Kivuli Pump Station | 2026-07-11 | 100% | 186 | 186
KPS-RFC-0060 | KPS-01-01 | Main Power Generation - Subsystem 01-01 | Kivuli Pump Station | 2026-07-12 | 100% | 33 | 33
KPS-RFC-0080 | KPS-03-02 | HV Power Distribution - Subsystem 03-02 | Kivuli Pump Station | 2026-07-14 | 100% | 16 | 16
KPS-RFC-0090 | KPS-03-03 | HV Power Distribution - Subsystem 03-03 | Kivuli Pump Station | 2026-07-26 | 100% | 12 | 12
KPS-RFC-0140 | KPS-08-04 | ICSS & Control Systems - Subsystem 08-04 | Kivuli Pump Station | 2026-07-30 | 100% | 113 | 113
KPS-RFC-0100 | KPS-03-04 | HV Power Distribution - Subsystem 03-04 | Kivuli Pump Station | 2026-07-31 | 100% | 18 | 18
KPS-RFC-0130 | KPS-08-03 | ICSS & Control Systems - Subsystem 08-03 | Kivuli Pump Station | 2026-07-31 | 100% | 8 | 8
KPS-RFC-0200 | KPS-63-01 | Potable & Utility Water - Subsystem 63-01 | Kivuli Pump Station | 2026-08-02 | 88.89% | 24 | 27
KPS-RFC-0150 | KPS-53-01 | Fired Heaters - Subsystem 53-01 | Kivuli Pump Station | 2026-08-05 | 42.42% | 14 | 33
KPS-RFC-0180 | KPS-53-03 | Fired Heaters - Subsystem 53-03 | Kivuli Pump Station | 2026-08-05 | 42.86% | 6 | 14
KPS-RFC-0110 | KPS-08-01 | ICSS & Control Systems - Subsystem 08-01 | Kivuli Pump Station | 2026-08-07 | 56.36% | 31 | 55
KPS-RFC-0230 | KPS-09-01 | Fire & Gas Detection - Subsystem 09-01 | Kivuli Pump Station | 2026-08-07 | 70% | 14 | 20
KPS-RFC-0120 | KPS-08-02 | ICSS & Control Systems - Subsystem 08-02 | Kivuli Pump Station | 2026-08-09 | 44.26% | 27 | 61
KPS-RFC-0160 | KPS-53-02 | Fired Heaters - Subsystem 53-02 | Kivuli Pump Station | 2026-08-12 | 82.35% | 14 | 17
KPS-RFC-0190 | KPS-62-02 | Diesel Fuel - Subsystem 62-02 | Kivuli Pump Station | 2026-08-14 | 55.56% | 15 | 27
KPS-RFC-0170 | KPS-08-05 | ICSS & Control Systems - Subsystem 08-05 | Kivuli Pump Station | 2026-08-17 | 100% | 33 | 33
KPS-RFC-0270 | KPS-28-02 | Mainline Pumps - Subsystem 28-02 | Kivuli Pump Station | 2026-08-18 | 70% | 14 | 20
KPS-RFC-0240 | KPS-28-01 | Mainline Pumps - Subsystem 28-01 | Kivuli Pump Station | 2026-08-20 | 33.33% | 5 | 15
KPS-RFC-0220 | KPS-08-06 | ICSS & Control Systems - Subsystem 08-06 | Kivuli Pump Station | 2026-08-22 | 57.78% | 26 | 45
KPS-RFC-0300 | KPS-28-04 | Mainline Pumps - Subsystem 28-04 | Kivuli Pump Station | 2026-08-23 | 78.57% | 11 | 14
KPS-RFC-0210 | KPS-06-02 | Lighting & Small Power - Subsystem 06-02 | Kivuli Pump Station | 2026-08-27 | 100% | 25 | 25
KPS-RFC-0250 | KPS-25-01 | Metering - Subsystem 25-01 | Kivuli Pump Station | 2026-08-27 | 100% | 54 | 54
KPS-RFC-0260 | KPS-25-02 | Metering - Subsystem 25-02 | Kivuli Pump Station | 2026-08-29 | 45.95% | 17 | 37
KPS-RFC-0350 | KPS-61-01 | Instrument & Utility Air - Subsystem 61-01 | Kivuli Pump Station | 2026-08-29 | 81.82% | 18 | 22
KPS-RFC-0280 | KPS-28-03 | Mainline Pumps - Subsystem 28-03 | Kivuli Pump Station | 2026-08-30 | 65.71% | 23 | 35
KPS-RFC-0320 | KPS-63-02 | Potable & Utility Water - Subsystem 63-02 | Kivuli Pump Station | 2026-08-31 | 58.18% | 32 | 55
KPS-RFC-0290 | KPS-0H-01 | Start-up Support Systems - Subsystem 0H-01 | Kivuli Pump Station | 2026-09-02 | 52% | 13 | 25
KPS-RFC-0310 | KPS-28-05 | Mainline Pumps - Subsystem 28-05 | Kivuli Pump Station | 2026-09-13 | 44.9% | 22 | 49
KPS-RFC-0370 | KPS-62-03 | Diesel Fuel - Subsystem 62-03 | Kivuli Pump Station | 2026-09-15 | 68.18% | 30 | 44
KPS-RFC-0380 | KPS-79-01 | Telecom - Subsystem 79-01 | Kivuli Pump Station | 2026-09-17 | 78.75% | 63 | 80
KPS-RFC-0330 | KPS-08-07 | ICSS & Control Systems - Subsystem 08-07 | Kivuli Pump Station | 2026-09-19 | 32.26% | 10 | 31
KPS-RFC-0340 | KPS-08-08 | ICSS & Control Systems - Subsystem 08-08 | Kivuli Pump Station | 2026-09-19 | 40.91% | 27 | 66
KPS-RFC-0360 | KPS-08-09 | ICSS & Control Systems - Subsystem 08-09 | Kivuli Pump Station | 2026-09-19 | 37.5% | 3 | 8
KPS-RFC-0400 | KPS-79-02 | Telecom - Subsystem 79-02 | Kivuli Pump Station | 2026-09-19 | 29.33% | 44 | 150
KPS-RFC-0390 | KPS-62-04 | Diesel Fuel - Subsystem 62-04 | Kivuli Pump Station | 2026-09-26 | 68% | 34 | 50
KPS-RFC-0450 | KPS-78-01 | Cathodic Protection - Subsystem 78-01 | Kivuli Pump Station | 2026-10-03 | 50% | 3 | 6
KPS-RFC-0420 | KPS-06-03 | Lighting & Small Power - Subsystem 06-03 | Kivuli Pump Station | 2026-10-04 | 50% | 8 | 16
KPS-RFC-0410 | KPS-61-02 | Instrument & Utility Air - Subsystem 61-02 | Kivuli Pump Station | 2026-10-07 | 41.67% | 10 | 24
KPS-RFC-0470 | KPS-84-01 | Warehouse & Workshops - Subsystem 84-01 | Kivuli Pump Station | 2026-10-10 | 62.5% | 10 | 16
KPS-RFC-0440 | KPS-02-01 | Emergency Diesel Generation - Subsystem 02-01 | Kivuli Pump Station | 2026-10-13 | 60.47% | 26 | 43
KPS-RFC-0430 | KPS-09-02 | Fire & Gas Detection - Subsystem 09-02 | Kivuli Pump Station | 2026-10-17 | 64.29% | 18 | 28
KPS-RFC-0480 | KPS-99-01 | Commissioning Support - Subsystem 99-01 | Kivuli Pump Station | 2026-10-27 | 59.09% | 13 | 22
KPS-RFC-0460 | KPS-83-01 | Control Buildings - Subsystem 83-01 | Kivuli Pump Station | 2026-11-01 | 44.44% | 4 | 9
MPR-RFC-0010 | MPR-62-01 | Diesel Fuel - Subsystem 62-01 | Mlima Pressure Reduction Station | 2026-05-20 | 100% | 147 | 147
MPR-RFC-0030 | MPR-61-01 | Instrument & Utility Air - Subsystem 61-01 | Mlima Pressure Reduction Station | 2026-05-21 | 60% | 15 | 25
MPR-RFC-0020 | MPR-63-01 | Potable & Utility Water - Subsystem 63-01 | Mlima Pressure Reduction Station | 2026-05-26 | 100% | 104 | 104
MPR-RFC-0040 | MPR-04-01 | LV Power Distribution - Subsystem 04-01 | Mlima Pressure Reduction Station | 2026-06-18 | 100% | 14 | 14
MPR-RFC-0050 | MPR-01-01 | Main Power Generation - Subsystem 01-01 | Mlima Pressure Reduction Station | 2026-06-21 | 100% | 73 | 73
MPR-RFC-0100 | MPR-61-02 | Instrument & Utility Air - Subsystem 61-02 | Mlima Pressure Reduction Station | 2026-07-08 | 100% | 18 | 18
MPR-RFC-0060 | MPR-09-01 | Fire & Gas Detection - Subsystem 09-01 | Mlima Pressure Reduction Station | 2026-07-11 | 100% | 93 | 93
MPR-RFC-0090 | MPR-28-01 | Mainline Pumps - Subsystem 28-01 | Mlima Pressure Reduction Station | 2026-07-13 | 100% | 58 | 58
MPR-RFC-0130 | MPR-08-03 | ICSS & Control Systems - Subsystem 08-03 | Mlima Pressure Reduction Station | 2026-07-19 | 100% | 92 | 92
MPR-RFC-0070 | MPR-08-01 | ICSS & Control Systems - Subsystem 08-01 | Mlima Pressure Reduction Station | 2026-07-23 | 100% | 60 | 60
MPR-RFC-0110 | MPR-03-01 | HV Power Distribution - Subsystem 03-01 | Mlima Pressure Reduction Station | 2026-07-24 | 100% | 126 | 126
MPR-RFC-0080 | MPR-08-02 | ICSS & Control Systems - Subsystem 08-02 | Mlima Pressure Reduction Station | 2026-07-24 | 100% | 45 | 45
MPR-RFC-0140 | MPR-61-03 | Instrument & Utility Air - Subsystem 61-03 | Mlima Pressure Reduction Station | 2026-08-05 | 64.29% | 9 | 14
MPR-RFC-0120 | MPR-05-01 | UPS & DC Systems - Subsystem 05-01 | Mlima Pressure Reduction Station | 2026-08-06 | 46.15% | 6 | 13
MPR-RFC-0170 | MPR-62-02 | Diesel Fuel - Subsystem 62-02 | Mlima Pressure Reduction Station | 2026-09-14 | 62.5% | 10 | 16
MPR-RFC-0160 | MPR-08-04 | ICSS & Control Systems - Subsystem 08-04 | Mlima Pressure Reduction Station | 2026-09-20 | 46.15% | 6 | 13
MPR-RFC-0150 | MPR-03-02 | HV Power Distribution - Subsystem 03-02 | Mlima Pressure Reduction Station | 2026-09-25 | 80% | 24 | 30
MPR-RFC-0180 | MPR-63-02 | Potable & Utility Water - Subsystem 63-02 | Mlima Pressure Reduction Station | 2026-09-28 | 74.49% | 184 | 247
MPR-RFC-0190 | MPR-79-01 | Telecom - Subsystem 79-01 | Mlima Pressure Reduction Station | 2026-09-29 | 44.68% | 42 | 94
MPR-RFC-0280 | MPR-08-07 | ICSS & Control Systems - Subsystem 08-07 | Mlima Pressure Reduction Station | 2026-10-08 | 67.74% | 21 | 31
MPR-RFC-0230 | MPR-28-02 | Mainline Pumps - Subsystem 28-02 | Mlima Pressure Reduction Station | 2026-10-08 | 76.92% | 20 | 26
MPR-RFC-0200 | MPR-03-03 | HV Power Distribution - Subsystem 03-03 | Mlima Pressure Reduction Station | 2026-10-10 | 66.67% | 12 | 18
MPR-RFC-0220 | MPR-25-02 | Metering - Subsystem 25-02 | Mlima Pressure Reduction Station | 2026-10-10 | 50% | 22 | 44
MPR-RFC-0290 | MPR-09-02 | Fire & Gas Detection - Subsystem 09-02 | Mlima Pressure Reduction Station | 2026-10-12 | 78.79% | 156 | 198
MPR-RFC-0260 | MPR-08-05 | ICSS & Control Systems - Subsystem 08-05 | Mlima Pressure Reduction Station | 2026-10-13 | 70% | 42 | 60
MPR-RFC-0210 | MPR-25-01 | Metering - Subsystem 25-01 | Mlima Pressure Reduction Station | 2026-10-14 | 59.84% | 76 | 127
MPR-RFC-0240 | MPR-03-04 | HV Power Distribution - Subsystem 03-04 | Mlima Pressure Reduction Station | 2026-10-15 | 32.65% | 16 | 49
MPR-RFC-0270 | MPR-08-06 | ICSS & Control Systems - Subsystem 08-06 | Mlima Pressure Reduction Station | 2026-10-20 | 73.17% | 60 | 82
MPR-RFC-0250 | MPR-06-01 | Lighting & Small Power - Subsystem 06-01 | Mlima Pressure Reduction Station | 2026-10-22 | 52.7% | 39 | 74
MPR-RFC-0330 | MPR-82-01 | Substations - Subsystem 82-01 | Mlima Pressure Reduction Station | 2026-10-23 | 59.62% | 31 | 52
MPR-RFC-0320 | MPR-63-03 | Potable & Utility Water - Subsystem 63-03 | Mlima Pressure Reduction Station | 2026-10-28 | 76.19% | 48 | 63
MPR-RFC-0300 | MPR-08-08 | ICSS & Control Systems - Subsystem 08-08 | Mlima Pressure Reduction Station | 2026-11-06 | 7.692% | 1 | 13
MPR-RFC-0310 | MPR-61-04 | Instrument & Utility Air - Subsystem 61-04 | Mlima Pressure Reduction Station | 2026-11-06 | 42.86% | 6 | 14
MPR-RFC-0340 | MPR-86-01 | Site Security - Subsystem 86-01 | Mlima Pressure Reduction Station | 2026-11-06 | 38.89% | 7 | 18
NPS-RFC-0020 | NPS-06-01 | Lighting & Small Power - Subsystem 06-01 | Namara Pump Station | 2026-04-08 | 100% | 19 | 19
NPS-RFC-0010 | NPS-63-01 | Potable & Utility Water - Subsystem 63-01 | Namara Pump Station | 2026-04-20 | 100% | 20 | 20
NPS-RFC-0030 | NPS-09-01 | Fire & Gas Detection - Subsystem 09-01 | Namara Pump Station | 2026-05-01 | 100% | 13 | 13
NPS-RFC-0090 | NPS-62-02 | Diesel Fuel - Subsystem 62-02 | Namara Pump Station | 2026-05-06 | 100% | 27 | 27
NPS-RFC-0040 | NPS-62-01 | Diesel Fuel - Subsystem 62-01 | Namara Pump Station | 2026-05-07 | 100% | 59 | 59
NPS-RFC-0080 | NPS-04-03 | LV Power Distribution - Subsystem 04-03 | Namara Pump Station | 2026-05-08 | 80.65% | 75 | 93
NPS-RFC-0110 | NPS-06-02 | Lighting & Small Power - Subsystem 06-02 | Namara Pump Station | 2026-05-12 | 84.62% | 11 | 13
NPS-RFC-0060 | NPS-04-02 | LV Power Distribution - Subsystem 04-02 | Namara Pump Station | 2026-05-13 | 100% | 260 | 260
NPS-RFC-0120 | NPS-61-01 | Instrument & Utility Air - Subsystem 61-01 | Namara Pump Station | 2026-05-18 | 68.42% | 13 | 19
NPS-RFC-0100 | NPS-63-02 | Potable & Utility Water - Subsystem 63-02 | Namara Pump Station | 2026-05-19 | 100% | 16 | 16
NPS-RFC-0070 | NPS-83-01 | Control Buildings - Subsystem 83-01 | Namara Pump Station | 2026-05-20 | 87.5% | 21 | 24
NPS-RFC-0050 | NPS-04-01 | LV Power Distribution - Subsystem 04-01 | Namara Pump Station | 2026-05-21 | 100% | 14 | 14
NPS-RFC-0170 | NPS-62-03 | Diesel Fuel - Subsystem 62-03 | Namara Pump Station | 2026-05-22 | 100% | 63 | 63
NPS-RFC-0130 | NPS-01-01 | Main Power Generation - Subsystem 01-01 | Namara Pump Station | 2026-05-23 | 100% | 88 | 88
NPS-RFC-0140 | NPS-03-01 | HV Power Distribution - Subsystem 03-01 | Namara Pump Station | 2026-05-23 | 59.62% | 31 | 52
NPS-RFC-0160 | NPS-61-02 | Instrument & Utility Air - Subsystem 61-02 | Namara Pump Station | 2026-05-24 | 100% | 22 | 22
NPS-RFC-0200 | NPS-53-01 | Fired Heaters - Subsystem 53-01 | Namara Pump Station | 2026-05-26 | 100% | 10 | 10
NPS-RFC-0150 | NPS-05-01 | UPS & DC Systems - Subsystem 05-01 | Namara Pump Station | 2026-05-30 | 100% | 55 | 55
NPS-RFC-0220 | NPS-61-03 | Instrument & Utility Air - Subsystem 61-03 | Namara Pump Station | 2026-06-06 | 100% | 14 | 14
NPS-RFC-0180 | NPS-01-02 | Main Power Generation - Subsystem 01-02 | Namara Pump Station | 2026-06-11 | 100% | 41 | 41
NPS-RFC-0190 | NPS-01-03 | Main Power Generation - Subsystem 01-03 | Namara Pump Station | 2026-06-14 | 100% | 94 | 94
NPS-RFC-0260 | NPS-08-01 | ICSS & Control Systems - Subsystem 08-01 | Namara Pump Station | 2026-06-15 | 100% | 14 | 14
NPS-RFC-0240 | NPS-01-04 | Main Power Generation - Subsystem 01-04 | Namara Pump Station | 2026-06-18 | 100% | 28 | 28
NPS-RFC-0230 | NPS-62-04 | Diesel Fuel - Subsystem 62-04 | Namara Pump Station | 2026-06-19 | 100% | 53 | 53
NPS-RFC-0280 | NPS-83-02 | Control Buildings - Subsystem 83-02 | Namara Pump Station | 2026-06-19 | 100% | 47 | 47
NPS-RFC-0210 | NPS-03-02 | HV Power Distribution - Subsystem 03-02 | Namara Pump Station | 2026-06-23 | 100% | 15 | 15
NPS-RFC-0270 | NPS-08-02 | ICSS & Control Systems - Subsystem 08-02 | Namara Pump Station | 2026-06-23 | 100% | 19 | 19
NPS-RFC-0330 | NPS-08-06 | ICSS & Control Systems - Subsystem 08-06 | Namara Pump Station | 2026-06-26 | 100% | 37 | 37
NPS-RFC-0350 | NPS-25-01 | Metering - Subsystem 25-01 | Namara Pump Station | 2026-06-26 | 100% | 77 | 77
NPS-RFC-0310 | NPS-08-05 | ICSS & Control Systems - Subsystem 08-05 | Namara Pump Station | 2026-06-29 | 100% | 18 | 18
NPS-RFC-0340 | NPS-08-07 | ICSS & Control Systems - Subsystem 08-07 | Namara Pump Station | 2026-06-30 | 100% | 68 | 68
NPS-RFC-0400 | NPS-28-03 | Mainline Pumps - Subsystem 28-03 | Namara Pump Station | 2026-06-30 | 100% | 10 | 10
NPS-RFC-0250 | NPS-01-05 | Main Power Generation - Subsystem 01-05 | Namara Pump Station | 2026-07-01 | 71.43% | 5 | 7
NPS-RFC-0290 | NPS-08-03 | ICSS & Control Systems - Subsystem 08-03 | Namara Pump Station | 2026-07-01 | 100% | 188 | 188
NPS-RFC-0300 | NPS-08-04 | ICSS & Control Systems - Subsystem 08-04 | Namara Pump Station | 2026-07-04 | 100% | 138 | 138
NPS-RFC-0320 | NPS-61-04 | Instrument & Utility Air - Subsystem 61-04 | Namara Pump Station | 2026-07-09 | 100% | 13 | 13
NPS-RFC-0360 | NPS-61-05 | Instrument & Utility Air - Subsystem 61-05 | Namara Pump Station | 2026-07-10 | 100% | 51 | 51
NPS-RFC-0450 | NPS-75-01 | HVAC - Subsystem 75-01 | Namara Pump Station | 2026-07-13 | 100% | 49 | 49
NPS-RFC-0480 | NPS-26-01 | Crude Storage - Subsystem 26-01 | Namara Pump Station | 2026-07-14 | 100% | 156 | 156
NPS-RFC-0460 | NPS-75-02 | HVAC - Subsystem 75-02 | Namara Pump Station | 2026-07-16 | 100% | 60 | 60
NPS-RFC-0490 | NPS-28-06 | Mainline Pumps - Subsystem 28-06 | Namara Pump Station | 2026-07-17 | 100% | 16 | 16
NPS-RFC-0410 | NPS-03-03 | HV Power Distribution - Subsystem 03-03 | Namara Pump Station | 2026-07-21 | 100% | 23 | 23
NPS-RFC-0370 | NPS-25-02 | Metering - Subsystem 25-02 | Namara Pump Station | 2026-07-21 | 100% | 61 | 61
NPS-RFC-0390 | NPS-28-02 | Mainline Pumps - Subsystem 28-02 | Namara Pump Station | 2026-07-21 | 100% | 28 | 28
NPS-RFC-0380 | NPS-28-01 | Mainline Pumps - Subsystem 28-01 | Namara Pump Station | 2026-07-22 | 100% | 25 | 25
NPS-RFC-0470 | NPS-08-08 | ICSS & Control Systems - Subsystem 08-08 | Namara Pump Station | 2026-07-23 | 100% | 11 | 11
NPS-RFC-0510 | NPS-71-01 | Firewater Pumps & Ring Main - Subsystem 71-01 | Namara Pump Station | 2026-07-26 | 100% | 106 | 106
NPS-RFC-0530 | NPS-79-01 | Telecom - Subsystem 79-01 | Namara Pump Station | 2026-07-26 | 91.75% | 89 | 97
NPS-RFC-0440 | NPS-28-05 | Mainline Pumps - Subsystem 28-05 | Namara Pump Station | 2026-07-28 | 100% | 25 | 25
NPS-RFC-0540 | NPS-25-04 | Metering - Subsystem 25-04 | Namara Pump Station | 2026-07-30 | 100% | 30 | 30
NPS-RFC-0500 | NPS-61-06 | Instrument & Utility Air - Subsystem 61-06 | Namara Pump Station | 2026-07-30 | 100% | 42 | 42
NPS-RFC-0420 | NPS-25-03 | Metering - Subsystem 25-03 | Namara Pump Station | 2026-07-31 | 61.49% | 91 | 148
NPS-RFC-0430 | NPS-28-04 | Mainline Pumps - Subsystem 28-04 | Namara Pump Station | 2026-07-31 | 100% | 54 | 54
NPS-RFC-0550 | NPS-79-02 | Telecom - Subsystem 79-02 | Namara Pump Station | 2026-08-09 | 50% | 17 | 34
NPS-RFC-0520 | NPS-03-04 | HV Power Distribution - Subsystem 03-04 | Namara Pump Station | 2026-08-12 | 90.7% | 39 | 43
NPS-RFC-0560 | NPS-82-01 | Substations - Subsystem 82-01 | Namara Pump Station | 2026-08-14 | 62% | 31 | 50
NPS-RFC-0580 | NPS-63-03 | Potable & Utility Water - Subsystem 63-03 | Namara Pump Station | 2026-08-15 | 66.67% | 14 | 21
NPS-RFC-0570 | NPS-06-03 | Lighting & Small Power - Subsystem 06-03 | Namara Pump Station | 2026-08-17 | 80.52% | 62 | 77
NPS-RFC-0630 | NPS-63-04 | Potable & Utility Water - Subsystem 63-04 | Namara Pump Station | 2026-08-27 | 65.52% | 19 | 29
NPS-RFC-0610 | NPS-62-05 | Diesel Fuel - Subsystem 62-05 | Namara Pump Station | 2026-09-01 | 91.15% | 237 | 260
NPS-RFC-0650 | NPS-63-05 | Potable & Utility Water - Subsystem 63-05 | Namara Pump Station | 2026-09-02 | 92% | 23 | 25
NPS-RFC-0620 | NPS-03-06 | HV Power Distribution - Subsystem 03-06 | Namara Pump Station | 2026-09-04 | 33.33% | 42 | 126
NPS-RFC-0600 | NPS-09-02 | Fire & Gas Detection - Subsystem 09-02 | Namara Pump Station | 2026-09-07 | 65.62% | 21 | 32
NPS-RFC-0660 | NPS-06-04 | Lighting & Small Power - Subsystem 06-04 | Namara Pump Station | 2026-09-10 | 51.11% | 23 | 45
NPS-RFC-0590 | NPS-03-05 | HV Power Distribution - Subsystem 03-05 | Namara Pump Station | 2026-09-11 | 77.08% | 37 | 48
NPS-RFC-0640 | NPS-62-06 | Diesel Fuel - Subsystem 62-06 | Namara Pump Station | 2026-09-12 | 48.48% | 16 | 33
NPS-RFC-0690 | NPS-84-01 | Warehouse & Workshops - Subsystem 84-01 | Namara Pump Station | 2026-09-20 | 75.61% | 31 | 41
NPS-RFC-0670 | NPS-53-02 | Fired Heaters - Subsystem 53-02 | Namara Pump Station | 2026-09-25 | 59.46% | 22 | 37
NPS-RFC-0700 | NPS-99-01 | Commissioning Support - Subsystem 99-01 | Namara Pump Station | 2026-09-27 | 59.26% | 16 | 27
NPS-RFC-0680 | NPS-82-02 | Substations - Subsystem 82-02 | Namara Pump Station | 2026-10-01 | 53.33% | 8 | 15
NPS-RFC-0710 | NPS-99-02 | Commissioning Support - Subsystem 99-02 | Namara Pump Station | 2026-10-12 | 29.27% | 12 | 41
NPS-RFC-0720 | NPS-99-03 | Commissioning Support - Subsystem 99-03 | Namara Pump Station | 2026-10-13 | 73.08% | 19 | 26
TPS-RFC-0020 | TPS-63-01 | Potable & Utility Water - Subsystem 63-01 | Tembea Pump Station | 2026-02-06 | 100% | 15 | 15
TPS-RFC-0010 | TPS-06-01 | Lighting & Small Power - Subsystem 06-01 | Tembea Pump Station | 2026-02-13 | 100% | 29 | 29
TPS-RFC-0030 | TPS-62-01 | Diesel Fuel - Subsystem 62-01 | Tembea Pump Station | 2026-02-14 | 100% | 22 | 22
TPS-RFC-0040 | TPS-04-01 | LV Power Distribution - Subsystem 04-01 | Tembea Pump Station | 2026-02-28 | 100% | 43 | 43
TPS-RFC-0070 | TPS-61-01 | Instrument & Utility Air - Subsystem 61-01 | Tembea Pump Station | 2026-03-04 | 100% | 88 | 88
TPS-RFC-0060 | TPS-09-01 | Fire & Gas Detection - Subsystem 09-01 | Tembea Pump Station | 2026-03-07 | 100% | 20 | 20
TPS-RFC-0090 | TPS-62-03 | Diesel Fuel - Subsystem 62-03 | Tembea Pump Station | 2026-03-15 | 100% | 82 | 82
TPS-RFC-0050 | TPS-03-01 | HV Power Distribution - Subsystem 03-01 | Tembea Pump Station | 2026-03-16 | 66.67% | 12 | 18
TPS-RFC-0100 | TPS-60-01 | Heat Tracing - Subsystem 60-01 | Tembea Pump Station | 2026-03-16 | 100% | 16 | 16
TPS-RFC-0080 | TPS-62-02 | Diesel Fuel - Subsystem 62-02 | Tembea Pump Station | 2026-03-20 | 100% | 73 | 73
TPS-RFC-0110 | TPS-60-02 | Heat Tracing - Subsystem 60-02 | Tembea Pump Station | 2026-04-07 | 100% | 13 | 13
TPS-RFC-0120 | TPS-60-03 | Heat Tracing - Subsystem 60-03 | Tembea Pump Station | 2026-04-08 | 100% | 20 | 20
TPS-RFC-0130 | TPS-71-01 | Firewater Pumps & Ring Main - Subsystem 71-01 | Tembea Pump Station | 2026-04-09 | 100% | 260 | 260
TPS-RFC-0140 | TPS-60-04 | Heat Tracing - Subsystem 60-04 | Tembea Pump Station | 2026-04-13 | 100% | 47 | 47
TPS-RFC-0170 | TPS-60-06 | Heat Tracing - Subsystem 60-06 | Tembea Pump Station | 2026-04-13 | 100% | 34 | 34
TPS-RFC-0160 | TPS-60-05 | Heat Tracing - Subsystem 60-05 | Tembea Pump Station | 2026-04-14 | 100% | 11 | 11
TPS-RFC-0150 | TPS-01-01 | Main Power Generation - Subsystem 01-01 | Tembea Pump Station | 2026-04-21 | 100% | 39 | 39
TPS-RFC-0190 | TPS-01-02 | Main Power Generation - Subsystem 01-02 | Tembea Pump Station | 2026-04-23 | 100% | 50 | 50
TPS-RFC-0200 | TPS-60-08 | Heat Tracing - Subsystem 60-08 | Tembea Pump Station | 2026-04-26 | 100% | 39 | 39
TPS-RFC-0180 | TPS-60-07 | Heat Tracing - Subsystem 60-07 | Tembea Pump Station | 2026-05-02 | 100% | 34 | 34
TPS-RFC-0260 | TPS-60-12 | Heat Tracing - Subsystem 60-12 | Tembea Pump Station | 2026-05-03 | 100% | 45 | 45
TPS-RFC-0210 | TPS-60-09 | Heat Tracing - Subsystem 60-09 | Tembea Pump Station | 2026-05-05 | 100% | 72 | 72
TPS-RFC-0250 | TPS-01-03 | Main Power Generation - Subsystem 01-03 | Tembea Pump Station | 2026-05-08 | 100% | 124 | 124
TPS-RFC-0220 | TPS-08-01 | ICSS & Control Systems - Subsystem 08-01 | Tembea Pump Station | 2026-05-12 | 100% | 54 | 54
TPS-RFC-0230 | TPS-60-10 | Heat Tracing - Subsystem 60-10 | Tembea Pump Station | 2026-05-12 | 100% | 24 | 24
TPS-RFC-0240 | TPS-60-11 | Heat Tracing - Subsystem 60-11 | Tembea Pump Station | 2026-05-14 | 100% | 39 | 39
TPS-RFC-0270 | TPS-60-13 | Heat Tracing - Subsystem 60-13 | Tembea Pump Station | 2026-05-15 | 100% | 11 | 11
TPS-RFC-0300 | TPS-60-14 | Heat Tracing - Subsystem 60-14 | Tembea Pump Station | 2026-05-16 | 100% | 30 | 30
TPS-RFC-0320 | TPS-60-16 | Heat Tracing - Subsystem 60-16 | Tembea Pump Station | 2026-05-18 | 73.68% | 14 | 19
TPS-RFC-0310 | TPS-60-15 | Heat Tracing - Subsystem 60-15 | Tembea Pump Station | 2026-05-20 | 91.03% | 71 | 78
TPS-RFC-0290 | TPS-08-03 | ICSS & Control Systems - Subsystem 08-03 | Tembea Pump Station | 2026-05-24 | 100% | 37 | 37
TPS-RFC-0330 | TPS-60-17 | Heat Tracing - Subsystem 60-17 | Tembea Pump Station | 2026-05-24 | 100% | 32 | 32
TPS-RFC-0360 | TPS-60-19 | Heat Tracing - Subsystem 60-19 | Tembea Pump Station | 2026-05-25 | 100% | 14 | 14
TPS-RFC-0280 | TPS-08-02 | ICSS & Control Systems - Subsystem 08-02 | Tembea Pump Station | 2026-05-30 | 100% | 23 | 23
TPS-RFC-0340 | TPS-05-01 | UPS & DC Systems - Subsystem 05-01 | Tembea Pump Station | 2026-06-05 | 100% | 26 | 26
TPS-RFC-0350 | TPS-60-18 | Heat Tracing - Subsystem 60-18 | Tembea Pump Station | 2026-06-11 | 100% | 46 | 46
TPS-RFC-0380 | TPS-60-20 | Heat Tracing - Subsystem 60-20 | Tembea Pump Station | 2026-06-15 | 100% | 12 | 12
TPS-RFC-0410 | TPS-61-02 | Instrument & Utility Air - Subsystem 61-02 | Tembea Pump Station | 2026-06-16 | 100% | 51 | 51
TPS-RFC-0390 | TPS-60-21 | Heat Tracing - Subsystem 60-21 | Tembea Pump Station | 2026-06-21 | 78.57% | 22 | 28
TPS-RFC-0370 | TPS-05-02 | UPS & DC Systems - Subsystem 05-02 | Tembea Pump Station | 2026-06-22 | 100% | 28 | 28
TPS-RFC-0430 | TPS-60-24 | Heat Tracing - Subsystem 60-24 | Tembea Pump Station | 2026-06-23 | 100% | 44 | 44
TPS-RFC-0400 | TPS-60-22 | Heat Tracing - Subsystem 60-22 | Tembea Pump Station | 2026-06-24 | 100% | 16 | 16
TPS-RFC-0420 | TPS-60-23 | Heat Tracing - Subsystem 60-23 | Tembea Pump Station | 2026-06-28 | 100% | 147 | 147
TPS-RFC-0450 | TPS-60-26 | Heat Tracing - Subsystem 60-26 | Tembea Pump Station | 2026-06-28 | 100% | 42 | 42
TPS-RFC-0490 | TPS-60-29 | Heat Tracing - Subsystem 60-29 | Tembea Pump Station | 2026-07-03 | 100% | 39 | 39
TPS-RFC-0470 | TPS-60-28 | Heat Tracing - Subsystem 60-28 | Tembea Pump Station | 2026-07-07 | 100% | 25 | 25
TPS-RFC-0440 | TPS-60-25 | Heat Tracing - Subsystem 60-25 | Tembea Pump Station | 2026-07-08 | 100% | 21 | 21
TPS-RFC-0460 | TPS-60-27 | Heat Tracing - Subsystem 60-27 | Tembea Pump Station | 2026-07-11 | 100% | 49 | 49
TPS-RFC-0480 | TPS-53-01 | Fired Heaters - Subsystem 53-01 | Tembea Pump Station | 2026-07-12 | 100% | 145 | 145
TPS-RFC-0520 | TPS-60-30 | Heat Tracing - Subsystem 60-30 | Tembea Pump Station | 2026-07-22 | 100% | 7 | 7
TPS-RFC-0510 | TPS-53-02 | Fired Heaters - Subsystem 53-02 | Tembea Pump Station | 2026-07-25 | 100% | 9 | 9
TPS-RFC-0500 | TPS-08-04 | ICSS & Control Systems - Subsystem 08-04 | Tembea Pump Station | 2026-08-03 | 100% | 38 | 38
TPS-RFC-0580 | TPS-03-03 | HV Power Distribution - Subsystem 03-03 | Tembea Pump Station | 2026-08-07 | 90.48% | 19 | 21
TPS-RFC-0530 | TPS-08-05 | ICSS & Control Systems - Subsystem 08-05 | Tembea Pump Station | 2026-08-08 | 54.17% | 13 | 24
TPS-RFC-0560 | TPS-71-04 | Firewater Pumps & Ring Main - Subsystem 71-04 | Tembea Pump Station | 2026-08-09 | 72.41% | 21 | 29
TPS-RFC-0540 | TPS-71-02 | Firewater Pumps & Ring Main - Subsystem 71-02 | Tembea Pump Station | 2026-08-10 | 75% | 33 | 44
TPS-RFC-0600 | TPS-08-06 | ICSS & Control Systems - Subsystem 08-06 | Tembea Pump Station | 2026-08-11 | 47.86% | 56 | 117
TPS-RFC-0650 | TPS-74-02 | Gaseous Fire Suppression - Subsystem 74-02 | Tembea Pump Station | 2026-08-14 | 50% | 10 | 20
TPS-RFC-0680 | TPS-53-04 | Fired Heaters - Subsystem 53-04 | Tembea Pump Station | 2026-08-15 | 87.8% | 36 | 41
TPS-RFC-0550 | TPS-71-03 | Firewater Pumps & Ring Main - Subsystem 71-03 | Tembea Pump Station | 2026-08-15 | 70.59% | 12 | 17
TPS-RFC-0630 | TPS-03-06 | HV Power Distribution - Subsystem 03-06 | Tembea Pump Station | 2026-08-18 | 47.06% | 24 | 51
TPS-RFC-0610 | TPS-74-01 | Gaseous Fire Suppression - Subsystem 74-01 | Tembea Pump Station | 2026-08-18 | 81.25% | 39 | 48
TPS-RFC-0570 | TPS-03-02 | HV Power Distribution - Subsystem 03-02 | Tembea Pump Station | 2026-08-23 | 59.83% | 70 | 117
TPS-RFC-0590 | TPS-03-04 | HV Power Distribution - Subsystem 03-04 | Tembea Pump Station | 2026-08-24 | 50% | 11 | 22
TPS-RFC-0640 | TPS-53-03 | Fired Heaters - Subsystem 53-03 | Tembea Pump Station | 2026-08-24 | 66.67% | 30 | 45
TPS-RFC-0690 | TPS-01-06 | Main Power Generation - Subsystem 01-06 | Tembea Pump Station | 2026-08-26 | 31.25% | 5 | 16
TPS-RFC-0660 | TPS-01-04 | Main Power Generation - Subsystem 01-04 | Tembea Pump Station | 2026-08-29 | 84.27% | 75 | 89
TPS-RFC-0670 | TPS-01-05 | Main Power Generation - Subsystem 01-05 | Tembea Pump Station | 2026-08-29 | 48.05% | 37 | 77
TPS-RFC-0710 | TPS-84-01 | Warehouse & Workshops - Subsystem 84-01 | Tembea Pump Station | 2026-08-30 | 47.22% | 17 | 36
TPS-RFC-0620 | TPS-03-05 | HV Power Distribution - Subsystem 03-05 | Tembea Pump Station | 2026-08-31 | 74.58% | 44 | 59
TPS-RFC-0700 | TPS-28-01 | Mainline Pumps - Subsystem 28-01 | Tembea Pump Station | 2026-09-02 | 84.91% | 45 | 53
TPS-RFC-0740 | TPS-75-01 | HVAC - Subsystem 75-01 | Tembea Pump Station | 2026-09-02 | 30.86% | 25 | 81
TPS-RFC-0760 | TPS-03-08 | HV Power Distribution - Subsystem 03-08 | Tembea Pump Station | 2026-09-09 | 48% | 24 | 50
TPS-RFC-0790 | TPS-62-04 | Diesel Fuel - Subsystem 62-04 | Tembea Pump Station | 2026-09-11 | 66.67% | 14 | 21
TPS-RFC-0730 | TPS-08-08 | ICSS & Control Systems - Subsystem 08-08 | Tembea Pump Station | 2026-09-13 | 32.26% | 10 | 31
TPS-RFC-0750 | TPS-03-07 | HV Power Distribution - Subsystem 03-07 | Tembea Pump Station | 2026-09-14 | 66.27% | 55 | 83
TPS-RFC-0780 | TPS-61-03 | Instrument & Utility Air - Subsystem 61-03 | Tembea Pump Station | 2026-09-16 | 76.07% | 89 | 117
TPS-RFC-0720 | TPS-08-07 | ICSS & Control Systems - Subsystem 08-07 | Tembea Pump Station | 2026-09-17 | 75.68% | 28 | 37
TPS-RFC-0800 | TPS-62-05 | Diesel Fuel - Subsystem 62-05 | Tembea Pump Station | 2026-09-21 | 25% | 3 | 12
TPS-RFC-0770 | TPS-02-01 | Emergency Diesel Generation - Subsystem 02-01 | Tembea Pump Station | 2026-09-24 | 60.61% | 20 | 33
TPS-RFC-0820 | TPS-79-01 | Telecom - Subsystem 79-01 | Tembea Pump Station | 2026-10-02 | 52.38% | 11 | 21
TPS-RFC-0880 | TPS-25-02 | Metering - Subsystem 25-02 | Tembea Pump Station | 2026-10-04 | 45.71% | 16 | 35
TPS-RFC-0840 | TPS-28-03 | Mainline Pumps - Subsystem 28-03 | Tembea Pump Station | 2026-10-04 | 76.92% | 20 | 26
TPS-RFC-0810 | TPS-28-02 | Mainline Pumps - Subsystem 28-02 | Tembea Pump Station | 2026-10-08 | 60% | 15 | 25
TPS-RFC-0830 | TPS-79-02 | Telecom - Subsystem 79-02 | Tembea Pump Station | 2026-10-10 | 60.55% | 66 | 109
TPS-RFC-0850 | TPS-79-03 | Telecom - Subsystem 79-03 | Tembea Pump Station | 2026-10-10 | 54.76% | 23 | 42
TPS-RFC-0860 | TPS-79-04 | Telecom - Subsystem 79-04 | Tembea Pump Station | 2026-10-10 | 70.56% | 139 | 197
TPS-RFC-0900 | TPS-25-04 | Metering - Subsystem 25-04 | Tembea Pump Station | 2026-10-14 | 30% | 6 | 20
TPS-RFC-0910 | TPS-71-05 | Firewater Pumps & Ring Main - Subsystem 71-05 | Tembea Pump Station | 2026-10-15 | 74.58% | 44 | 59
TPS-RFC-0940 | TPS-71-07 | Firewater Pumps & Ring Main - Subsystem 71-07 | Tembea Pump Station | 2026-10-25 | 70.37% | 38 | 54
TPS-RFC-0870 | TPS-25-01 | Metering - Subsystem 25-01 | Tembea Pump Station | 2026-10-26 | 75% | 6 | 8
TPS-RFC-0890 | TPS-25-03 | Metering - Subsystem 25-03 | Tembea Pump Station | 2026-10-27 | 54.55% | 36 | 66
TPS-RFC-0920 | TPS-28-04 | Mainline Pumps - Subsystem 28-04 | Tembea Pump Station | 2026-10-30 | 30.99% | 22 | 71
TPS-RFC-0930 | TPS-71-06 | Firewater Pumps & Ring Main - Subsystem 71-06 | Tembea Pump Station | 2026-10-30 | 37.5% | 15 | 40
TPS-RFC-0990 | TPS-08-10 | ICSS & Control Systems - Subsystem 08-10 | Tembea Pump Station | 2026-11-01 | 31.88% | 22 | 69
TPS-RFC-0980 | TPS-08-09 | ICSS & Control Systems - Subsystem 08-09 | Tembea Pump Station | 2026-11-11 | 21.43% | 3 | 14
TPS-RFC-1020 | TPS-06-02 | Lighting & Small Power - Subsystem 06-02 | Tembea Pump Station | 2026-11-13 | 25.93% | 7 | 27
TPS-RFC-0960 | TPS-99-01 | Commissioning Support - Subsystem 99-01 | Tembea Pump Station | 2026-11-14 | 42.11% | 8 | 19
TPS-RFC-0950 | TPS-71-08 | Firewater Pumps & Ring Main - Subsystem 71-08 | Tembea Pump Station | 2026-11-15 | 23.81% | 5 | 21
TPS-RFC-0970 | TPS-99-02 | Commissioning Support - Subsystem 99-02 | Tembea Pump Station | 2026-11-15 | 54.35% | 25 | 46
TPS-RFC-1010 | TPS-50-01 | Heating Medium - Subsystem 50-01 | Tembea Pump Station | 2026-11-18 | 15.79% | 6 | 38
TPS-RFC-1000 | TPS-28-05 | Mainline Pumps - Subsystem 28-05 | Tembea Pump Station | 2026-11-19 | 55.17% | 32 | 58
TPS-RFC-1030 | TPS-61-04 | Instrument & Utility Air - Subsystem 61-04 | Tembea Pump Station | 2026-12-02 | 22.03% | 13 | 59
TPS-RFC-1050 | TPS-82-01 | Substations - Subsystem 82-01 | Tembea Pump Station | 2026-12-04 | 36.36% | 8 | 22
TPS-RFC-1040 | TPS-03-09 | HV Power Distribution - Subsystem 03-09 | Tembea Pump Station | 2026-12-05 | 51.72% | 30 | 58
TPS-RFC-1060 | TPS-63-02 | Potable & Utility Water - Subsystem 63-02 | Tembea Pump Station | 2026-12-25 | 7.692% | 4 | 52
TPS-RFC-1070 | TPS-63-03 | Potable & Utility Water - Subsystem 63-03 | Tembea Pump Station | 2027-01-03 | 30% | 3 | 10
TPS-RFC-1100 | TPS-08-11 | ICSS & Control Systems - Subsystem 08-11 | Tembea Pump Station | 2027-01-04 | 32.14% | 9 | 28
TPS-RFC-1090 | TPS-82-02 | Substations - Subsystem 82-02 | Tembea Pump Station | 2027-01-10 | 42.86% | 18 | 42
TPS-RFC-1080 | TPS-09-02 | Fire & Gas Detection - Subsystem 09-02 | Tembea Pump Station | 2027-01-11 | 45.45% | 15 | 33
TPS-RFC-1110 | TPS-09-03 | Fire & Gas Detection - Subsystem 09-03 | Tembea Pump Station | 2027-01-12 | 29.55% | 13 | 44
TPS-RFC-1120 | TPS-86-01 | Site Security - Subsystem 86-01 | Tembea Pump Station | 2027-01-12 | 25.86% | 15 | 58
ZPS-RFC-0010 | ZPS-04-01 | LV Power Distribution - Subsystem 04-01 | Zawadi Pump Station | 2026-07-04 | 100% | 23 | 23
ZPS-RFC-0050 | ZPS-03-02 | HV Power Distribution - Subsystem 03-02 | Zawadi Pump Station | 2026-07-07 | 100% | 18 | 18
ZPS-RFC-0020 | ZPS-62-01 | Diesel Fuel - Subsystem 62-01 | Zawadi Pump Station | 2026-07-07 | 100% | 65 | 65
ZPS-RFC-0040 | ZPS-03-01 | HV Power Distribution - Subsystem 03-01 | Zawadi Pump Station | 2026-07-08 | 100% | 26 | 26
ZPS-RFC-0080 | ZPS-08-01 | ICSS & Control Systems - Subsystem 08-01 | Zawadi Pump Station | 2026-07-10 | 100% | 20 | 20
ZPS-RFC-0070 | ZPS-05-01 | UPS & DC Systems - Subsystem 05-01 | Zawadi Pump Station | 2026-07-14 | 100% | 26 | 26
ZPS-RFC-0030 | ZPS-28-01 | Mainline Pumps - Subsystem 28-01 | Zawadi Pump Station | 2026-07-17 | 77.69% | 94 | 121
ZPS-RFC-0120 | ZPS-04-02 | LV Power Distribution - Subsystem 04-02 | Zawadi Pump Station | 2026-07-22 | 100% | 147 | 147
ZPS-RFC-0060 | ZPS-62-02 | Diesel Fuel - Subsystem 62-02 | Zawadi Pump Station | 2026-07-25 | 100% | 91 | 91
ZPS-RFC-0130 | ZPS-08-04 | ICSS & Control Systems - Subsystem 08-04 | Zawadi Pump Station | 2026-07-30 | 100% | 81 | 81
ZPS-RFC-0150 | ZPS-28-02 | Mainline Pumps - Subsystem 28-02 | Zawadi Pump Station | 2026-07-30 | 100% | 12 | 12
ZPS-RFC-0100 | ZPS-08-02 | ICSS & Control Systems - Subsystem 08-02 | Zawadi Pump Station | 2026-08-02 | 100% | 23 | 23
ZPS-RFC-0090 | ZPS-53-01 | Fired Heaters - Subsystem 53-01 | Zawadi Pump Station | 2026-08-06 | 84.62% | 11 | 13
ZPS-RFC-0110 | ZPS-08-03 | ICSS & Control Systems - Subsystem 08-03 | Zawadi Pump Station | 2026-08-07 | 60% | 15 | 25
ZPS-RFC-0140 | ZPS-25-01 | Metering - Subsystem 25-01 | Zawadi Pump Station | 2026-08-08 | 42.86% | 21 | 49
ZPS-RFC-0180 | ZPS-25-02 | Metering - Subsystem 25-02 | Zawadi Pump Station | 2026-08-10 | 81.82% | 9 | 11
ZPS-RFC-0210 | ZPS-62-03 | Diesel Fuel - Subsystem 62-03 | Zawadi Pump Station | 2026-08-12 | 66.67% | 14 | 21
ZPS-RFC-0240 | ZPS-99-01 | Commissioning Support - Subsystem 99-01 | Zawadi Pump Station | 2026-08-13 | 47.06% | 16 | 34
ZPS-RFC-0270 | ZPS-62-04 | Diesel Fuel - Subsystem 62-04 | Zawadi Pump Station | 2026-08-17 | 35.62% | 52 | 146
ZPS-RFC-0160 | ZPS-63-01 | Potable & Utility Water - Subsystem 63-01 | Zawadi Pump Station | 2026-08-18 | 59.76% | 49 | 82
ZPS-RFC-0290 | ZPS-08-07 | ICSS & Control Systems - Subsystem 08-07 | Zawadi Pump Station | 2026-08-20 | 63.64% | 21 | 33
ZPS-RFC-0300 | ZPS-62-05 | Diesel Fuel - Subsystem 62-05 | Zawadi Pump Station | 2026-08-22 | 86.67% | 52 | 60
ZPS-RFC-0250 | ZPS-08-05 | ICSS & Control Systems - Subsystem 08-05 | Zawadi Pump Station | 2026-08-25 | 52.63% | 10 | 19
ZPS-RFC-0220 | ZPS-0H-01 | Start-up Support Systems - Subsystem 0H-01 | Zawadi Pump Station | 2026-08-25 | 100% | 35 | 35
ZPS-RFC-0170 | ZPS-63-02 | Potable & Utility Water - Subsystem 63-02 | Zawadi Pump Station | 2026-08-25 | 79.17% | 38 | 48
ZPS-RFC-0190 | ZPS-79-01 | Telecom - Subsystem 79-01 | Zawadi Pump Station | 2026-08-25 | 34.96% | 43 | 123
ZPS-RFC-0280 | ZPS-08-06 | ICSS & Control Systems - Subsystem 08-06 | Zawadi Pump Station | 2026-08-28 | 75% | 18 | 24
ZPS-RFC-0200 | ZPS-25-03 | Metering - Subsystem 25-03 | Zawadi Pump Station | 2026-08-28 | 100% | 8 | 8
ZPS-RFC-0340 | ZPS-75-01 | HVAC - Subsystem 75-01 | Zawadi Pump Station | 2026-08-31 | 100% | 119 | 119
ZPS-RFC-0260 | ZPS-63-03 | Potable & Utility Water - Subsystem 63-03 | Zawadi Pump Station | 2026-09-01 | 80% | 8 | 10
ZPS-RFC-0230 | ZPS-28-03 | Mainline Pumps - Subsystem 28-03 | Zawadi Pump Station | 2026-09-02 | 36.28% | 41 | 113
ZPS-RFC-0320 | ZPS-63-04 | Potable & Utility Water - Subsystem 63-04 | Zawadi Pump Station | 2026-09-02 | 82.35% | 14 | 17
ZPS-RFC-0310 | ZPS-62-06 | Diesel Fuel - Subsystem 62-06 | Zawadi Pump Station | 2026-09-10 | 75% | 27 | 36
ZPS-RFC-0390 | ZPS-78-01 | Cathodic Protection - Subsystem 78-01 | Zawadi Pump Station | 2026-09-12 | 29.41% | 20 | 68
ZPS-RFC-0370 | ZPS-08-08 | ICSS & Control Systems - Subsystem 08-08 | Zawadi Pump Station | 2026-09-14 | 76.92% | 10 | 13
ZPS-RFC-0330 | ZPS-62-07 | Diesel Fuel - Subsystem 62-07 | Zawadi Pump Station | 2026-09-16 | 66.22% | 49 | 74
ZPS-RFC-0410 | ZPS-84-01 | Warehouse & Workshops - Subsystem 84-01 | Zawadi Pump Station | 2026-09-19 | 66.67% | 4 | 6
ZPS-RFC-0380 | ZPS-09-01 | Fire & Gas Detection - Subsystem 09-01 | Zawadi Pump Station | 2026-09-21 | 42.86% | 6 | 14
ZPS-RFC-0440 | ZPS-75-02 | HVAC - Subsystem 75-02 | Zawadi Pump Station | 2026-09-21 | 53.33% | 8 | 15
ZPS-RFC-0350 | ZPS-91-01 | Drainage - Subsystem 91-01 | Zawadi Pump Station | 2026-09-23 | 42.11% | 8 | 19
ZPS-RFC-0430 | ZPS-61-01 | Instrument & Utility Air - Subsystem 61-01 | Zawadi Pump Station | 2026-09-25 | 29.17% | 7 | 24
ZPS-RFC-0360 | ZPS-62-08 | Diesel Fuel - Subsystem 62-08 | Zawadi Pump Station | 2026-09-26 | 79.17% | 38 | 48
ZPS-RFC-0400 | ZPS-08-09 | ICSS & Control Systems - Subsystem 08-09 | Zawadi Pump Station | 2026-09-28 | 27.27% | 6 | 22
ZPS-RFC-0460 | ZPS-09-02 | Fire & Gas Detection - Subsystem 09-02 | Zawadi Pump Station | 2026-10-04 | 70% | 7 | 10
ZPS-RFC-0450 | ZPS-03-03 | HV Power Distribution - Subsystem 03-03 | Zawadi Pump Station | 2026-10-05 | 69.23% | 27 | 39
ZPS-RFC-0420 | ZPS-79-02 | Telecom - Subsystem 79-02 | Zawadi Pump Station | 2026-10-08 | 30.77% | 8 | 26

## How to use
Commissioning Systems Skyline - input file
One row = one subsystem with an RFC (Ready For Commissioning) milestone.
Replace the sample rows with your own data. Keep the sheet name 'Skyline'
and the exact column headers on row 1 of that sheet.
Activity ID: the RFC activity ID from your schedule (P6 or other).
Subsystem ID: unique subsystem tag. Also the label shown on each skyline box.
Subsystem Description: free text, shown in tooltips only.
Station: site / area / plant the subsystem belongs to. Drives the slicer.
RFC Date: planned RFC date. The skyline stacks subsystems by week of this date.
RFC Progress %: formula, ITRs Closed / Total ITRs. Do not overwrite with values.
ITRs Closed / Total ITRs: inspection test records signed vs total for the subsystem.
All rows in this sample are fictitious (stations, IDs, dates, counts).